## seu-sprint
Week | Task | Sub-steps/Notes | Estimated Effort (hrs) | Status | Notes
1 | Improve Martha AI pathing | Enhance navigation and obstacle avoidance. | 1 | Backlog
1 | Add catch radius | Implement forgiveness mechanic for throws. | 1 | Backlog
1 | Add sorting pause | UI toggle for pausing sorting section. | 0.5 | Backlog
1 | Add encouraging feedback | Success messages on key actions. | 1 | Backlog
1 | Add mini achievement system | Implement trackers for "First Match", "Perfect Throw", etc. with pop-ups. | 3 | Backlog
1 | Add story intro | Short text or cinematic sequence. | 1 | Backlog
1 | Add touchscreen basics | Gesture mapping for accessibility. | 2 | Backlog
2 | Add 3 levels + backgrounds | Add level 7, 8, 9 | 3 | Backlog
2 | True Pixel Art updates | Convert sprites/UI to authentic style. | 3 | Backlog
2 | Improve tutorial | Animated tooltips | 2 | Backlog
2 | UI/UX polish | Refine level select, sorting, throwing, score screens. | 3 | Backlog
2 | Sound/music enhancements | Improve SFX and loopable tracks. | 2 | Backlog
3 | Progressive Difficulty | Easy default; unlock +1/+2/+3/+4 modes post-clear. 1) Save flag. 2) Parametrize speed. 3) UI menu. | 5 | Backlog
3 | GFL App Integration | 1) Export test build. 2) Map inputs. 3) Test embedding. Requirement: Platform docs. | 3.5 | Backlog
3 | Marketing Materials | Screenshots, trailer, 1-page pitch. | 2.5 | Backlog
4 | Full QA/Testing | 1) Checklist playthroughs. 2) Beta testers. 3) Balance tweaks. | 5 | Backlog
4 | Expand Animations | Expand run, add idle | 3 | Backlog

## Sheet1
Status
Backlog
Active
Research
Review
Complete